## Estimation Template User Guide
Guidelines for Effort Estimation Template - For each task, consider research, discussion time, planning, personal review, review with others, and verification activities. Please note any assumptions made in determining your estimates. These can be placed into the comments field for each task.
Unit of Size: This is the unit used to define the relative size of a project. For example: number of requirements, no of test cases etc.
Time per Unit Size: How much time, in hours, you estimate would be required for each unit of size.
Total Amount: The amount of time required which is equal to unit of size multply with time per unit size.
Complexity: A pre-defined number determined as follows:
· 1.0 = A low level of complexity
· 1.5 = A medium level of complexity
· 2.0 = A high level of complexity
Staff Skill Level: A pre-defined number determined as follows:
· 1.0 = The person performing this task is a staff member with extensive experience with the process and with the project
· 1.5 = The person performing this task is a staff member with some prior experience with the process and with the project
· 2.0 = The person performing this task has little experience with the process or with the project
Rework: A pre-defined number that indicates the expected level of rework anticipated for this project given the complexity and skill levels for this task. This number is determined as follows:
· 1.0 = The anticipated rework level is low
· 1.5 = The anticipated rework level is medium
· 2.0 = The anticipated rework level is high
Effort in Hours: A calculated figure determined by the following algorithm:
(((Time per Unit Size * Total Size) * Complexity) * Staff Skill Level) * Rework = Effort in Hours.
For example:
Take a task with a unit of size in requirement document that contains 50 requirements. If you estimate each reqiement to take 2 hours for a person who has extensive experience with the project, and you determine the complexity of this task to be high, and you anticipate the rework effort to be medium you would come up with an Effort in Hours figure of 300 by plugging the appropriate values into the algorithm. Your figures would be as follows:
Time per Unit of Size = 2
Total Size = 50
Complexity = 2
Staff Skill Level = 1
Rework = 1.5
((((2 * 50) * 2) * 1) * 1.5) =
((100 *2) * 1) * 1.5 =
(200 * 1) * 1.5 =
200 * 1.5 = 300

## Estimation Template
EFFORT ESTIMATION TEMPLATE
| PROJECT NAME: | [7 empty] | PROJECT # | TWMS
| ESTIMATOR: |  |  | Bala Segu |  |  |  |  | DATE: | 20-09-2008
| Versions Estimates Based upon: |  |  | EFFORT = (((total size * time per unit size) * complexity) * Staff Skill Level) * rework.
1. ESTIMATE TESTING STAFF HOURS
|  |  |  | Unit of Size |  |  | Time per Unit Size
| ID* | Module or Supporting Activity | % work | Simple | Medium | High | Simple | Medium | High | Total Amount | Complexity | Staff Skill Level | Rework | TOTAL Effort in Hours | TOTAL Effort in Days(6.5Hr/Per Day) | TOTAL Effort in Days(8.0Hr/Per Day) | % of Distrbn
|  | Project Initiation:Assessment | [12 empty] | 0 | 0 | 0
|  | Understand Business Requirements |  | 2 | 5 | 3 | 2 | 2.5 | 3.33 | 26.49 | 1 | 1 | 1.5 | 39.735 | 6.11 | 4.97 | 34.25
|  | Plan | [12 empty] | 0 | 0 | 0
|  | Analyze/Review Business Requirements |  | 2 | 5 | 3 | 2 | 2.5 | 3.33 | 26.49 | 1 | 1 | 1.5 | 39.735 | 6.11 | 4.97 | 34.25
|  | Prepare Test plan & Strategy (% of Analyze/Review Business Requirements) | 10 | - | - | - | - | - | - | - | 1 | 1 | 1 | 3.9735 | 0.61 | 0.5 | 3.45
|  | Test Design | [12 empty] | 0 | 0 | 0
|  | Test plan review, update and Sign off (half of % Test Plan & Strategy) | 5 | - | - | - | - | - | - | - | 1 | 1 | 1 | 0.19867 | 0.03 | 0.02 | 0.14
|  | Develop detailed system test cases | . | 6 | 20 | 15 | 0.3 | 0.45 | 0.55 | 19.05 | 1.5 | 1 | 1.5 | 12.8588 | 1.98 | 1.61 | 11.1
|  | Prepare Requirements Traceability Matrix (% of Test Cases) | 30 | - | - | - | - | - | - | - | - | - | - | 3.8576 | 0.59 | 0.48 | 3.31
|  | Internal And external test case review, update and sign off (% of Develop test cases) | 10 | - | - | - | - | - | - | - | - | - | - | 1.2859 | 0.2 | 0.16 | 1.1
|  | Internal And external test case review updates and sign off (% of Develop test cases) | 15 | - | - | - | - | - | - | - | - | - | - | 1.9288 | 0.3 | 0.24 | 1.65
|  | Test data preparation and setup (% of develop test cases) | 25 | - | - | - | - | - | - | - | - | - | - | 3.2147 | 0.49 | 0.4 | 2.76
|  | Complete Environment and Data Set-up, obtain all the data necessary for testing, execute programs for test data | 1 | - | - | - | - | - | - | - | - | - | - |  |  |  | 0
|  | Smoke - Pre QA Test Execution | [12 empty] | 0 | 0 | 0
|  | Execute Pre-System Test * No of cycles | 2 | 0.24 | 1.6 | 1.5 | 0.15 | 0.2 | 0.4 | 0.956 | 1.5 | 1 | 1 | 0.4302 | 0.07 | 0.05 | 0.34
|  | Defect Logging & Fixing |  | 0.24 | 1.6 | 1.5 | 0.15 | 0.2 | 0.25 | 0.731 | 1.5 | 1 | 1 | 0.16448 | 0.03 | 0.02 | 0.14
|  | System - Test Execution | [12 empty] | 0 | 0 | 0
|  | Execute System Test cases * No of cycles | 2 | 6 | 20 | 15 | 0.15 | 0.2 | 0.4 | 10.9 | 1.5 | 1 | 1.5 | 7.3575 | 1.13 | 0.92 | 6.34
|  | Defect Logging & Fixing * No of cycles | 1 | 0.36 | 1.6 | 1.5 | 0.15 | 0.2 | 0.25 | 0.749 | 1.5 | 1 | 1 | 0.16853 | 0.03 | 0.02 | 0.14
|  | Regression - Test Execution | [12 empty] | 0 | 0 | 0
|  | Execute Regression (% of Execute System Test Cases) | 25 | - | - | - | - | - | - | - | - | - | 1.5 | 0.91969 | 0.14 | 0.11 | 0.76
|  | Defect Logging & Fixing |  | 0.36 | 1.6 | 1.5 | 0.15 | 0.2 | 0.25 | 0.749 | 1.5 | 1 | 1.5 | 0.25279 | 0.04 | 0.03 | 0.21
|  | Updates | [12 empty] | 0 | 0 | 0
|  | Test Results Consolidation, defect report, report results | 10 | [10 empty] | 0.058579 | 0.01 | 0.01 | 0.07
|  | Meetings - Status Meetings, Brain Storming sessions, Planning meetings, Internal Meeting etc | 10 | - | - | - | - | - | - | - | - | - | - | 11.614 | 1.79 | 1.45 | 9.99
Project Activities
|  | Process Control (% of Analyze/Review Business Requirements) | 10 | [10 empty] | 3.9735 | 0.61 | 0.5 | 3.45
|  | Total Effort (in hours) | [11 empty] | 116.0811 | 17.86 | 14.51 | 100
2. LIST ALL ESTIMATING ASSUMPTIONS
Estimates have been arrived at considering the following documentation/inputs:
| 1 | Standard testing activities and deliverables
| 2 | Business Requirements Documentation as of 01-JULY-07
Note on E9: bala.segu: Team agrees on the unit of size, e.g. number of requirementss, number of test cases etc.
Note on H9: bala.segu: How much time (in hours or % of hours) is required to execute each unit of size? For example, it could take 1 hour to understand or to write test cases or to execute one test case.
Note on K10: The total amount required which is equal to unit of size multply with time per unit size.
Note on L10: High = 2 Medium = 1.5 Average = 1
Note on M10: Little Experience = 2 Some Experience = 1.5 Extensive Experience= 1
Note on N10: High = 2 Medium = 1.5 Low = 1
Note on O10: EFFORT = (((total size * time per unit size) * complexity) * learning curve) * unknowns.

## Header
No of TC's per Requirement
| Simple |  |  | Medium |  |  | High
| Optimistic | Most Likely | Pessimistic | Optimistic | Most Likely | Pessimistic | Optimistic | Most Likely | Pessimistic | Simple | Medium | High | Average
Test Cases | 2 | 3 | 4 | 3 | 4 | 5 | 4 | 5 | 6 | 3 | 4 | 5 | 4
Hours for
| Simple |  |  | Medium |  |  | High
| Optimistic | Most Likely | Pessimistic | Optimistic | Most Likely | Pessimistic | Optimistic | Most Likely | Pessimistic | Simple | Medium | High | Average | Percentage
Understanding Requirements | 1 | 2 | 3 | 1.5 | 2.5 | 3.5 | 2.5 | 3.5 | 4 | 2 | 2.5 | 3.33 | 2.61
Analyse/Review Requirements | 1 | 2 | 3 | 1.5 | 2.5 | 3.5 | 2.5 | 3.5 | 4 | 2 | 2.5 | 3.33 | 2.61
Test Planning per TC | 0.25 | 0.3 | 0.35 | 0.4 | 0.45 | 0.5 | 0.5 | 0.55 | 0.6 | 0.3 | 0.45 | 0.55 | 0.43
Test Execution per TC | 0.1 | 0.15 | 0.2 | 0.15 | 0.2 | 0.25 | 0.3 | 0.4 | 0.5 | 0.15 | 0.2 | 0.4 | 0.25
Defect logging, Fixing per TC | 0.1 | 0.15 | 0.2 | 0.15 | 0.2 | 0.25 | 0.2 | 0.25 | 0.3 | 0.15 | 0.2 | 0.25 | 0.2
Automation - Test data Preparation & SetUp | [9 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Automation Functional | [9 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Automation - Performance | [9 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
% of Test Cases
| Simple |  |  | Medium |  |  | High
| Optimistic | Most Likely | Pessimistic | Optimistic | Most Likely | Pessimistic | Optimistic | Most Likely | Pessimistic | Simple | Medium | High | Average
Execute Pre System Test Cases | 3 | 4 | 5 | 7 | 8 | 9 | 9 | 10 | 11 | 4 | 8 | 10 | 7.33
Execute System Test Cases | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Defect logging for Pre System/Sanity Test and Exploratory defects | 3 | 4 | 5 | 7 | 8 | 9 | 9 | 10 | 11 | 4 | 8 | 10 | 7.33
Defect logging for System/Regression Test (Including Exploratory) | 5 | 6 | 7 | 7 | 8 | 9 | 9 | 10 | 11 | 6 | 8 | 10 | 8
Activity | Percentage
Project Activities of ? | 10
Project and Team management
QA Tools selection, planning & set up
KT, brainstorming, ramp up and team discussion sessions
Regular & Weekly Status Meetings
Meeting with others, Planning meetings, Internal Meeting etc
Process Control of ? | 5
Configuration management and Process tailoring
Build Metrics

## RequirementsSummary
|  |  | No of Complexity |  |  | No of TCs
Module | Sub Modules | No. of Requirements | Simple | Medium | High | Simple | Medium | High
M1 | [5 empty] | 0 | 0 | 0
| M01 | 10 | 2 | 5 | 3 | 6 | 20 | 15
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
|  |  | 2 | 5 | 3 | 6 | 20 | 15
Total Number |  |  |  |  | 10 |  |  | 41

## TestingType
|  |  | No of Complexity |  |  | Actual Total Smoke & Regression TCs |  |  | Actual No of Sanity TCs |  |  | Actual No Of Regression TCs
Module Name | Sub Module | No. of Requirements | Simple | Medium | High | Simple | Medium | High | Simple | Medium | High | Simple | Medium | High
M2
| M02 | 15 | 2 | 10 | 3 | 10 | 20 | 30 | 10 | 10 | 15 | 0 | 10 | 15
Total Number |  |  | 2 | 10 | 3 | 10 | 20 | 30 | 10 | 10 | 15 | 0 | 10 | 15
15

## -¦-
This page has been left blank intentionally. This is a separator page.